TASKLIST II

PANEL INTERVIEWS FOR TRIBUNALS SCHEDULED FOR 8TH TO 16TH JULY, 2026

| TASK | TIMELINE | PERSON RESPONSIBLE |
| --- | --- | --- |
| PREPARATION STAGE |  |  |
| Supervisor | Immediate | Mr. Wamaasa |
| Coordinator | Immediate | Mr. Amkaya |
| Scoresheets and sample questions | Immediate | Mr. Wamaasa/Mr. Amkaya/Mr. Aruwa |
| Invitation letters to shortlisted candidates. |  | Faith/Sylvia |
| Calling and sending texts to the candidates on the positions to be interviewed, dates and venues for the interviews (by 25th June, 2026) | Immediate | Mr. Omusamia Moses Ms. Ndigiti Wilter Ms. Sylvia Njeri Mr. Eugene Wesala Ms. Anisa Abdi Ms. Beatrice Gitonga Ms. Emmy Chepkemoi Ms. Lydia Obara Mr. Kaniaru Kabiru |
| Communicating, printing emails relating to interviews, responding to any communication |  | Ms. Nditika Ms. Gacheri |
| Preparation of interview schedules | immediate | Mr. Udali |
| Writing to vetting bodies |  | Mr. Udali |
| Following up reports from vetting bodies | immediate | Mr. Udali |
| Profiles for the Candidates in line with the approved schedule(s) | Immediate | Ms. Ndegwa/Ms. Kellong/Udali |
| Secretaries to the Panels | During interviews | Panel 1 – Mr. Wamaasa Isaac Panel 2 – Ms. Rebecca Kiplagat |
| Filling bio data forms and verifications of certificates and testimonials Assisting Secretaries/Coordinators in the Panels Positions | During interviews | Panel 1 - 8.7.2026 Member, Micro and Small Enterprises Tribunal Advocate - Patricia/Wilter - 9.7.2026 Member, Micro and Small Enterprises Tribunal Advocate – Eugene/Udali - 13.7.2026 Member, Micro and Small Enterprises Tribunal – Non-Advocate - Anisa/Faith - 14.7.2026 Member, Micro and Small Enterprises Tribunal – Non-Advocate – Emmy/Patricia - 15.7.2026 Member, Competition Tribunal – Vivien/ Beatrice - 16.7.2026 Deputy Director, Research and Policy- Omusamia/Faith PANE 2 - 8.7.2026 Member, Energy and Petroleum Tribunal – Faith/ Sylvia - 9.7.2026 Member, Energy and Petroleum Tribunal – Jane/Sylvia - 13.7.2026 Member, Energy and Petroleum Tribunal – Lydia/Udali - 14.7.2026 Member, Industrial Property Tribunal – Vivien/Omusamia - 15.7.2026 Member, Retirement Benefits Appeals Tribunal- Patricia/Kaniaru - 16.7.2026 Member, Retirement Benefits Appeals Tribunal- Udali/Wilter |
| ICT documentation and uploading to Ipads and scanning of interview documents | 2 days before interviews | Mr. Nzuki/Mr. Omusamia |
| Arrangement of the Boardroom and all the logistics | Immediate | Ms. Nditika Ms. Gitonga Ms. Ndigiti |
| Tea, Snacks, Confectionaries and stationery | During interviews | Procurement Unit and Mrs. Ndigiti/Ms. Obara |
| Reference materials, records and its logistics | During interviews | Mr. Kahui Ms. Nditika |
| Payments | After Interviews | Accounts Unit |
| Communication of results of the Interview to the successful candidates | After Interviews | JSC HRM Unit JSC Board Unit |
| Communication of results of the Interview to the unsuccessful candidates | After Interviews | Ms. Nditika Ms. Mwenda |
| Report Writing | After Interviews | JSC HRM Unit JSC Board Unit |

Isaac J.M. Wamaasa, (Mr.)

ACTING REGISTRAR,

JUDICIAL SERVICE COMMISSION

22nd June, 2026